## Hindrance log
Construction hindrance and delay log
One row per hindrance. The first thirteen columns are the fields of a SuperWise Issue; the last three are sheet-only.
Issue type | Title | Description | Status | Priority | Opened by | Opened on | Responsible | Targeted closure date | Resolved on | Closed on | Location | WBS task | Days open | Delay to the work (days) | Impact
Formulas:
Days open = IF([Opened on]="","",IF([Closed on]<>"",[Closed on],IF([Resolved on]<>"",[Resolved on],TODAY()))-[Opened on])

## Summary
Hindrance summary
By status
Open
InProgress
Resolved
Rejected
Closed
By priority
Low
Medium
High
Critical
Totals
Hindrances logged
Delay to the work (days)

## Instructions
How to use: Construction hindrance and delay log
1 | One row per hindrance. A hindrance is an Issue in the product, so the first thirteen columns are the fields of an Issue.
2 | Write a title that names the event, such as "Pile machine breakdown", and put the cause and the work stopped in the description.
3 | Status and priority are dropdowns with the product values. Set Resolved on when the cause is fixed and Closed on when it is signed off.
4 | Link each row to the WBS task it held up. Without that link a delay cannot be tied to the schedule.
5 | Days open is a formula. Delay to the work is the number of days you assess the hindrance cost the task. Impact is a short note. These three columns are sheet-only: the product does not store them.
6 | The Summary sheet counts rows by status and priority and adds up the delay days.
7 | Attach photos and letters outside this file, and note the reference in the description.
Field names follow the SuperWise product. Free template from superwise.site/templates/construction-hindrance-delay-log/, version v1.